## Sheet1
Feature List | Priority | Dependencies | Cost to Implement
Learn basics of React Native | 0 |  | 3 days
Mapping Display | 1 | Google maps api | 1 day
User controllable Settings | 2 |  | 2 days
Toggle Off Button | 1 |  | 1 day
User Selected Distance setting | 3 |  | 2 days
Prediction | 0 | Weather API (Dark Sky, national weather service, open weather map?) | 5 days
Preset route monitoring | 3 | ??? | 5 days
Locations (past/current) | 1 |  | 1 day
Feedback | 4 |  | 1 day
Notifications | 0 |  | 2 days